## Slide 1
THESIS EXECUTION FRAMEWORK
Retrieval-Grounded Arabic Fact-Checking
A step-by-step plan: from dataset recovery to a released retrieval benchmark
Karam Ahmad Kassem · Advisor: Dr. Shady Elbassuoni · American University of Beirut

## Slide 2
The Framework, At a Glance
Six sequential phases — each one builds on and validates the one before it
0
Data
Recovery
1
Retrieval
Layer
2
Verification
on Retrieval
3
Ensemble
Model
4
Robustness
Audit
5
Integration
& Writing
Core contribution: Phase 1 (Retrieval Layer) · Phases 3–4 make the result trustworthy · Phase 5 ships it
The question this framework answers:
Can a model find its own evidence for an Arabic claim — not just judge evidence it's handed — and can we prove the answer it gives is actually grounded in what it retrieved?

## Slide 3
PHASE 0 · Weeks 1–3
Data Recovery — Confirm the Foundation
GOAL
Confirm
Usable Data
make sure the raw materials actually support the plan
1
Download and inspect ARAFA
Pull the dataset from Zenodo. Confirm each claim still links to its original Wikipedia source chunk, and that the refutation mutation-type label is preserved.
2
Download and clean Arabic Wikipedia
Get the full dump, strip templates/links/category tags — same preprocessing ARAFA's own paper used.
3
Set up compute access
Confirm cluster access with Dr. Shady, or set up a rented GPU (Octopus/Colab) as a fallback for later phases.
DELIVERABLE:
A confirmed, usable dataset + a cleaned Wikipedia corpus ready to be chunked into passages.

## Slide 4
PHASE 1 · Weeks 4–11
Build & Evaluate the Retrieval Layer
CORE CONTRIBUTION
Retrieval
Benchmark
the main, reusable piece of this thesis
1
Chunk Wikipedia into passages
Split into retrieval-sized passages (~100–400 words), separate from ARAFA's larger generation-time chunks.
2
Match each claim to its gold passage
Use ARAFA's preserved source-chunk metadata to establish ground truth for every claim.
3
Build BM25 + dense + hybrid retrieval
Lexical index (BM25), dense index (multilingual embeddings via FAISS), and a fused hybrid version.
4
Evaluate retrieval on its own
Recall@1/5/10 and MRR against the known gold passage — before verification is even touched.
5
(Stretch) Fine-tune the retriever
If time allows, fine-tune a bi-encoder on claim→gold-passage pairs with hard negatives.
DELIVERABLE:
A benchmarked, released retrieval index — the artifact future researchers can reuse directly.

## Slide 5
PHASE 2 · Weeks 12–15
Verify Claims Using Retrieved Evidence
GOAL
Oracle vs.
Real Gap
quantify what retrieval errors actually cost
1
Bring in the verification models
Reuse or retrain AraBERTv2, AraModernBert, Llama-3.1-8B, and Qwen2.5-7B under comparable settings.
2
Run the oracle setting
Gold evidence given directly — this reproduces the original ARAFA paper's 77% F1 ceiling.
3
Run the pipeline setting
Same claims, but evidence now comes from Phase 1's retriever — with real retrieval errors included.
4
Compare the two
Report the performance gap — this number is the honest cost of removing the oracle assumption.
DELIVERABLE:
A clear, quantified table: verification performance with gold evidence vs. with retrieved evidence.

## Slide 6
PHASE 3 · Weeks 16–19
Build the Ensemble Verifier
GOAL
Beat the
Single Model
combine complementary strengths under real conditions
1
Collect per-claim signals
Gather each model's prediction, confidence, and the retriever's confidence score for every claim.
2
Train a gating / meta-classifier
A lightweight model (logistic regression or small NN) that learns which verifier to trust per claim.
3
Evaluate under the pipeline setting
Compare the ensemble against the strongest single model — specifically where evidence is imperfect, since that's where the gap should matter most.
DELIVERABLE:
An ensemble model shown to outperform any single verifier once evidence is retrieved, not given.

## Slide 7
PHASE 4 · Weeks 20–22
Audit for Shortcut Learning & Evidence Attribution
GOAL
Prove It's
Real Reasoning
make sure results reflect evidence use, not memorization
1
Closed-book baseline
Strip evidence entirely — how much accuracy comes from memorized knowledge alone?
2
Retrieval-success split
Compare accuracy on claims where retrieval found the right passage vs. where it didn't.
3
Perturbation & counterfactual tests
Swap in a random passage, then a contradicting one — does the model's answer actually change?
4
Per-mutation-type breakdown
Check refutation accuracy across all 5 mutation strategies to flag which are genuinely hard vs. easy giveaways.
DELIVERABLE:
A documented attribution protocol proving — or disproving — that the model is truly evidence-grounded.

## Slide 8
PHASE 5 · Weeks 23–28+
Integration, Writing & Release
GOAL
Ship the
Final System
a usable pipeline, not just isolated experiments
1
Combine everything into one pipeline
Claim in → retrieved evidence → verification label → confidence score, end to end.
2
Run final full-pipeline evaluation
One clean set of headline numbers covering retrieval, verification, and the ensemble together.
3
Release code, index & eval scripts
Public release so the retrieval benchmark is actually reusable by others — not just described in the thesis.
4
Write up and prepare defense
Full thesis document, results discussion, and defense materials.
DELIVERABLE:
The completed thesis, plus a public, reusable Arabic retrieval-augmented fact-checking benchmark.

## Slide 9
Timeline Summary
Approximately 28 weeks (~7 months) end to end — adjustable based on cluster access and scope decisions
P0
Data Recovery
Weeks 0-1
P1
Retrieval Layer
Weeks 1-3
P2
Verification on Retrieval
Weeks 3-4
P3
Ensemble Model
Weeks 4-6
P4
Robustness Audit
Weeks 6-8
P5
Integration & Writing
Weeks 8-10
Milestone check-ins with Dr. Shady are suggested at the end of each phase — confirming direction before moving to the next reduces the risk of rework.